## Defect Tracking Log
DEFECT TRACKING LOG - TRAINER MANAGEMENT SYSTEM
Project Name |  |  |  | Trainer Management System
Program Manager |  |  |  | Batch 2 - Group 7
Project Manager |  |  |  | Batch 2 - Group 7
Purpose: To ensure that the work product meets specifications for performance, defects must be tracked and fixed. These defects may arise from any Phase, but the majority will arise in the Testing Phase and must be properly captured and tracked through resolution. This form will allow documentation of test defects that must be corrected prior to project completion. Also, this form makes it easier to monitor status of the defect correction progress. This form may be used by any member of the software development team.
< Hover by the red triangle in the top left corner for more detail. Use the Instructions on the next tab to fill out fields.>
Defect No. | Date Created | Created By | Defect Description | PM Process | Lifecycle Phase | Priority | Owner | Assigned Date | Estimated Time to Fix | Status | Resolution | Resolution Date | Actual Time to Fix | Root Cause | Status | Priority | PM | Lifecycle Phase
1 | 2022-03-06 | Betsy | Can Approve a Trainer without selecting the employment type. | Executing/Controlling | Testing | High | Developing Team | 2022-03-06 | 6 days | New |  |  |  |  | New
2 | 2022-03-06 | Betsy | No Mail notification received while rejecting a application. | Executing/Controlling | Testing | High | Developing Team | 2022-03-07 | 6 days | New |  |  |  |  | Under Review | High | Opportunity Assessment | Opportunity Assessment
3 | 2022-03-07 | Betsy | While searching for a name, all words which is having the searched letter combination is being displayed | Executing/Controlling | Testing | Medium | Developing Team | 2022-03-08 | 6 days | New |  |  |  |  | In Progress | Medium | Initiating | Concept
4 | 2022-03-06 | Shyma | Text Displayed in the Home Page cannot be readable due to baground video | Executing/Controlling | Testing | Low | Developing Team | 2022-03-06 | 8 days | New |  |  |  |  | Completed | Low | Planning | Requirements
5 | 2022-03-06 | Shyma | No link Provided against the courses displayed in the Home Page | Executing/Controlling | Testing | Low | Developing Team | 2022-03-06 | 8 days | New | [6 empty] | Executing/Controlling | Design
6 | 2022-03-06 | Shyma | Courses listed in the Choose course dropdownlist is not matching with the courses given in the Home Page | Executing/Controlling | Testing | Medium | Developing Team | 2022-03-07 | 6 days | New | [6 empty] | Closing | Development
7 | 2022-03-07 | Shyma | SignUp by using the Keyboard keys(Enter,tab ,Arrow keys), Couldnot navigate through the courses listed using Arrow keys | Executing/Controlling | Testing | High | Developing Team | 2022-03-07 | 6 days | New | [7 empty] | Testing
8 | 2022-03-07 | Shyma | SignUp using already registered Email id | Executing/Controlling | Testing | High | Developing Team | 2022-03-07 | 6 days | New
9 | 2022-03-08 | Shyma | Submit button for SignUp should not be enabled without selecting the ICTAK Course | Executing/Controlling | Testing | High | Developing Team | 2022-03-08 | 6 days | New
10 | 2022-03-06 | Megha | Trainer Profile image is not displayed on Trainer Profile Information | Executing/Controlling | Testing | Medium | Developing Team | 2022-03-07 | 5 days | New | [7 empty] | Documentation and Training
11 | 2022-03-06 | Megha | Name' and 'Email' should not be able to change in Edit Trainer Profile since they are unique attributes and unchangeable. | Executing/Controlling | Testing | High | Developing Team | 2022-03-07 | 5 days | New |  |  | \ |  |  |  |  | Deployment
12 | 2022-03-08 | Neethu | Project name in all pages are incorrect .-"Trainers Mangement System" and Spelling errors found in Home page | Executing/Controlling | Testing | High | Developing Team | 2022-08-03 | 5days | New | [7 empty] | Post-Deployment
13 | 2022-08-03 | Neethu | Facebook link is not navigating to Facebook Homepage | Executing/Controlling | Testing | Low | Developing Team | 2022-08-03 | 5days | New
14 | 2022-08-03 | Neethu | Twitter link is not navigating to Twitter Homepage | Executing/Controlling | Testing | Low | Developing Team | 2022-08-03 | 5days | New
15 | 2022-08-03 | Neethu | Instagram link is not navigating to Instagram Homepage | Executing/Controlling | Testing | Low | Developing Team | 2022-08-03 | 5days | New
16 | 2022-03-08 | Anu | Allocate Button is not visible unless scrolled horizontally in the Trainer List. Also the horizontal scroll bar is not present. in the page. | Executing/Controlling | Testing | Medium | Developing Team | 2022-08-03 | 5 days | New
17 | 2022-03-18 | Anu | Trainer calendar is not blocked for the allocated period. Trainer can be alloted within an already allocated period many times. Trainer can be alloted in past time | Executing/Controlling | Testing | High | Developing Team | 2022-03-18 | 5 days | New
18 | 2022-03-19 | Megha | Trainer Allocation details are not displayed correctly while browser window is restored down | Executing/Controlling | Testing | Low | Developing Team | 2022-03-19 | 6 days | New
19 | 2022-03-19 | Megha | Data is not displayed when trainer allocation details page scrolling using keyboard while browser window is restored down | Executing/Controlling | Testing | Low | Developing Team | 2022-03-19 | 6 days | New
Note on E10: Choose from the drop down box.
Note on F10: Choose from the drop down box.
Note on G10: Choose from the drop down list
Note on K10: Choose from the drop down list.

## Defect Tracking Log Instruc
Defect Tracking Log Instructions
Field | Description
Defect Number | Unique identifier for the defect, i.e., 1,2 etc.
Date Created | Date on which the defect was initially reported and logged.
Created By | Name of the person who reported the defect.
Defect Description | Description of the defect. State the subsystem, area, or other part of the product in which the defect occurs or which is affected by the defect.
PM Process | Choose the Project Management Process this defect was reported for: Opportunity Assessment, Initiating, Planning, Executing/Controlling and Closing.
Lifecycle Phase | List the lifecycle this defect was reported for. The Software Development lifecycle is: Opportunity Assessment, Concept, Requirements, Design, Development, Testing, Documentation and Training, Deployment and Post Deployment.
Priority | The priority code indicates the impact of this defect on the project:
H = High (extremely important, the project cannot be successful without this defect being resolved)
M = Medium (important to project success, but a work around exists)
L = Low (desirable, but with little impact to project success if the defect is not resolved)
Owner | Name of the person who is responsible for fixing the defect.
Assigned Date | Date on which the defect was assigned for resolution.
Estimated Time To Fix | Estimated amount of time required to correct the defect. If applicable list in hours, not days.
Status | Current status of the defect: New, In Progress, Under Review and Completed.
Resolution | Description of the defect’s resolution.
Resolution Date | Date on which the defect is to be resolved (or is resolved depending upon its status).
Actual Time to Fix | Actual time required to correct the defect.
Root Cause Description | State the cause of the defect (for example, communication, oversight, transcription, education, process, bad code.).