## Metrics
TEST PROCESS METRICS
Total Requirements VS Total Test Cases |  | Total Bugs Raised VS Closed Per Period
Total Requirements | Total TC's
6 | 93
Total Time spent on Preperation VS Estimated Time |  | Total Bugs Closed VS Reopened Per Period
TC's Estimated Time | TC's Preperation Time
7 days | 10 days
Total TC Executed VS Planned |  | Bug Distribution Totals by Functional Areas/Requirements by Severity per period
Planned | Executed
93 Test Cases | 93 Test Cases
TCs Executed - Passed, Failed, Blocked
TCs Executed | 93
TCs Passed | 74
TCs Failed | 19
Total Time spent on Execution VS Estimated Time
Execution Estimated Time | Execution Actual Time
7 days | 10 days
TEST PRODUCT METRICS
Bug Distribution Totals by Functional Areas/Requirements by Severity per period
Total Requirements | 6
Total Major Severity | 8
Total Medium Severity | 5
Total Minor Severity | 3
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.